## Projektnachverfolgung
Projektnachverfolgung
| Kennzeichnen bei Prozentsatz Über-/Unterschreitung: | 70%
Projekt | Kategorie | Zugewiesen an | Geschätzter Anfang | Geschätztes Ende | Geschätzter Arbeitsaufwand (in Stunden) | Geschätzte Dauer (in Tagen) | Ist- Anfang | Ist- Ende | Kennzeichnungssymbol für Über-/Unterschreitung der Ist-Arbeit (in Stunden) | Ist-Arbeit (in Stunden) | Kennzeichnungssymbol für Über-/Unterschreitung der Ist-Dauer (in Tagen) | Ist-Dauer (in Tagen) | Notizen
SRS | Dokumentation | Andreas Mikula | 2019-04-29 | 2019-06-30 | 10 | 61 | 2019-04-29 | 2019-06-26 | 0 | 9.5 | 0 | 57
Definition GIT issues | Dokumentation | Andreas Mikula | 2019-03-25 | 2019-06-30 | 10 | 95 | 2019-03-25 | 2019-03-25 | 0 | 5 |  | 0
Definition GIT milestones | Dokumentation | Andreas Mikula | 2019-03-25 | 2019-06-30 | 10 | 95 | 2019-03-25 | 2019-03-25 | 0 | 5 |  | 0
Setup OS Raspberry Pi 2 | RASPI | Andreas Mikula | 2019-03-08 | 2019-03-10 | 4 | 2 | 2019-03-08 | 2019-03-08 | 0 | 4 |  | 0 | Installation -> Noobs 3.0
Grundgerüst TIVA | TIVA | Andreas Mikula | 2019-04-28 | 2019-05-15 | 25 | 17 | 2019-04-29 | 2019-05-30 | 0 | 34 | 1 | 31
Setup Tiva TCPEcho | TIVA | Andreas Mikula | 2019-04-28 | 2019-05-05 | 25 | 7 | 2019-04-28 | 2019-05-26 | 1 | 45 | 1 | 28
Setup server.c @ Raspi | RASPI | Andreas Mikula | 2019-03-28 | 2019-03-28 | 3 | 0 | 2019-03-28 | 2019-03-28 | 0 | 3 |  | 0
TCP Stream from client2srv | Testcases | Andreas Mikula | 2019-04-15 | 2019-06-28 | 50 | 73 | 2019-04-29 | 2019-05-26 | 0 | 55 | 0 | 27
HTTP Post Request for server impl | RASPI | Andreas Mikula | 2019-06-10 | 2019-06-30 | 40 | 20 | 2019-06-27 | 2019-06-28 | 0 | 14 | 1 | 1
SETUP

## Protokoll_Mikula
Date | from | to | Difference | To Do | Steps | Infos | Troubles | Fixes
2019-03-04 | 17:50 | 21:00 | 3:10 | Brainstorming while LV | define project setup & timepath
2019-03-08 | 11:30 | 13:15 | 1:45 | Raspi OS Install | * OS Noobs 3.0 Download
* Format SD with SD Formatter 4.0
* Copy Noobs to SD Card
[5 empty] | * OS Setup & Installation |  | Troubles with boot sequence: "sh: can't access tty" | "disable safemode" for correct boot mode
2019-03-17 | 17:00 | 18:15 | 1:15 | Raspi OS Config | * get latest updates
* first tests with environment
2019-03-18 | 17:50 | 21:00 | 3:10 | Recherche TCP/UDP Communication | * Online Recherche
2019-03-28 | 9:00 | 13:00 | 4:00 | Setup first client/server tests | * Implement client.c | First tests with server <-> client communication on Raspi
[5 empty] | * Implement server.c | First tests with server <-> client communication on Raspi
2019-03-29 | 8:00 | 8:30 | 0:30 | SD Card of Raspi brokes down |  | No possibility to save data permanent | * permanent saving of data is impossible
* reinstall OS is not possible
* formating of the SD card is not possible
* contacting lab to get new SD card
2019-04-01 | 16:00 | 16:30 | 0:30 | Meeting at lab with Mr Wambera | * getting another Tiva Board
[5 empty] | * troubleshooting with failured SD card | Got new SD card because of defect hardware
| 17:00 | 19:30 | 2:30 | Meeting with Schinewitz & Milli | * project status | divided work into two sub-parts
> 1. communication between boards (Mikula & Schinewitz)
> 2. setup microphone (Milli & Albrecht)
* reinstalling Noobs on Raspi
2019-04-28 | 11:00 | 16:00 | 5:00 | Setup TCP echo task | * getting Tiva ready for config
* setup Board_initEMAC()
[5 empty] | * setup TCPEcho_Task() |  | problems with .cgf file
[5 empty] | * testing pings from Raspi to Tiva | ping test from Raspi to Tiva are successful
2019-04-29 | 8:00 | 9:30 | 1:30 | Establish file Projektnachverfolgung.xlsx | * getting hand notices into excel file
| 12:30 | 14:00 | 1:30 | Brainstorming and online research
| 17:50 | 21:00 | 3:10 | Network between Tiva & Raspi
2019-05-20 | 17:50 | 21:00 | 3:10 | Network between Tiva & Raspi
2019-05-23 | 18:00 | 20:30 | 2:30 | Teammeeting | * communicate next steps
2019-05-26 | 10:00 | 10:30 | 0:30 | Enroll Projektnachverfolgung for all group members | * setup cloud access
| 11:00 | 13:00 | 2:00 | Start SRS | * design and content setup
| 13:30 | 20:00 | 6:30 | Network communication between Tiva & Raspi | * datastream from tiva to raspi | connection from Tiva to Raspi established | took a long time to recognize that DHCP service have to shut up manually
2019-05-27 | 18:00 | 19:30 | 1:30 | Working on SRS
2019-06-10 | 13:00 | 14:30 | 1:30 | sending infinite datastream from tiva client to raspi server | * setup new server.c
|  |  | 0:00 |  | * do changes on tcp_client.c
2019-06-16 | 14:00 | 15:45 | 1:45 | install & configure lighttpd on raspi to work as a webserver | * upate & upgrade raspberry board
|  |  | 0:00 |  | * install lighttpd
|  |  | 0:00 |  | * first tests with webserver
| 16:00 | 18:30 | 2:30 | testing http post |  |  | raspberry os hang. After newstart no OS.
2019-06-17 | 18:00 | 20:30 | 2:30 | Reinstall Raspberry after second SD error
2019-06-24 | 17:30 | 21:00 | 3:30 | setting up micpos.html for getting http post requests | * setup
|  |  | 0:00 |  | * tests
2019-06-25 | 19:00 | 23:00 | 4:00 | SRS | * writing on SRS
2019-06-26 | 17:00 | 19:00 | 2:00 | SRS | * finalizing SRS
2019-06-27 | 18:00 | 23:59 | 5:59 | HTTP Post Request Java2PHP on Raspberry | * setup http post request in java for server impl
|  |  | 0:00 |  | * convert string from server impl for onscreen output |  | can't get string from java server
2019-06-28 | 8:30 | 10:00 | 1:30 | Editing projektverfolgung.xlsx
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## Protokoll_Milli
Date | from | to | Difference | To Do | Steps | Infos | Troubles | Fixes
2019-03-04 | 17:50 | 21:00 | 3:10 | Brainstorming while LV | define project setup & timepath
2019-03-09 | 13:00 | 17:00 | 4:00 | Research about project | * communication types research
* implementation research
[5 empty] | * research for the main purpose | how to find the position of the voice
2019-03-16 | 16:00 | 18:00 | 2:00 | Setup code composer studio
setup TI-RTOS
2019-03-18 | 17:50 | 21:00 | 3:10 | Research for TCP/UDP Communication | * Online research
2019-04-01 | 17:00 | 19:30 | 2:30 | Meeting with Schinewitz & Mikula | * project status | divided work into two sub-parts
* 1. communication between boards (Mikula & Schinewitz)
* 2. setup microphone (Milli & Albrecht)
* receipt of microphones
2019-04-13 | 13:00 | 17:00 | 4:00 | Meeting with Albrecht | discuss and first step of the configuration of ADC
*check all needed ADC functions
*some tries to check how it works
2019-04-29 | 17:50 | 21:00 | 3:10 | Configuration of ADC | configure the ADC |  | receipt of error messages | discuss with lecturer and colleagues
*ADC port and pins config
2019-05-02 | 18:00 | 21:00 | 3:00 | Configuration of UART | configure the UART |  | works not properly | after discuss with the lector, create a task and problem is solved
*UART port config
2019-05-11 | 11:00 | 15:00 | 4:00 | Mailbox implementation | implement the mailbox |  | send value is not equal to received value
2019-05-17 | 18:00 | 21:00 | 3:00 | configuration for get value from microphone | to get logic values from microphones |  | high or low level voice get always same value
2019-05-20 | 17:50 | 21:00 | 3:10 | debug code for get value from mic.
2019-05-23 | 18:00 | 20:30 | 2:30 | Teammeeting | * communicate next steps
2019-06-04 | 16:30 | 18:00 | 1:30 | meeting with Schinewitz | test my software and hardware |  | hardware is defect (microphone) | order 2 new microphones
| 21:00 | 22:30 | 1:30 | css cant compare any code |  |  | . Error msg : cortex_m4_0 error connecting to the target | LM Flash Programmer TI : Debug port Unlock
2019-06-11 | 16:30 | 18:00 | 1:30 | brainstorming for Webinterface | discuss with colleagues for requirements
2019-06-15 | 12:00 | 18:00 | 6:00 | implementation of webinterface | *setup the webserver
*coding the webinterface
2019-06-24 | 17:50 | 21:00 | 3:10 | web interface on rasp. | test
get new microphones
|  |  |  | research for test cases | online research for test cases
2019-06-27 | 18:00 | 23:00 | 5:00 | working on test cases | *create test cases
*Prepare Testprotocol
2 microphones tested : OK
2019-06-28 | 18:00 | 22:00 | 4:00 | working on test cases | *run test cases
*write protocol
updated final version projektverfolgung

## Protokoll_Schinewitz
Date | from | to | Difference | To Do | Steps | Infos | Troubles | Fixes
2019-03-04 | 17:50 | 21:00 | 3:10 | Brainstorming | design project
2019-03-07 | 16:00 | 18:00 | 2:00 | Basic design | what happens in which order (do i need interrupts etc.)
2019-03-10 | 14:00 | 16:00 | 2:00 | Start SRS | Start SRS-Documentation
2019-03-18 | 17:50 | 21:00 | 3:10 | Tcp Client-Server connection | Build simple tcp-client
2019-04-01 | 17:00 | 19:30 | 2:30 | Team meeting | talk about progression and todos
2019-04-16 | 14:00 | 19:00 | 5:00 | Tcp Server-Client connection | Build simple tcp-server
2019-04-19 | 12:00 | 15:00 | 3:00 | Tcp Server-Client connection | Server debugging
2019-04-21 | 14:00 | 16:00 | 2:00 | Tcp Client-Server connection | Client debugging
2019-04-29 | 17:50 | 21:00 | 3:10 | tiva config
2019-05-03 | 12:00 | 18:00 | 6:00 | Tcp-server | **** it ! Let's build it in Java.
2019-05-06 | 17:50 | 21:00 | 3:10 | Test Tcp-connection
2019-05-17 | 15:00 | 20:00 | 5:00 | Microphon-Sensor | ADC - how does the microphone work? Etc.
2019-05-20 | 17:50 | 21:00 | 3:10 | Microphon-Sensor | get this thing to work |  | data makes no sense
2019-06-02 | 12:00 | 14:00 | 2:00 | Microphon-Sensor | how to get proper data from sensor…
2019-06-04 | 16:30 | 18:00 | 1:30 | Meet with Milli | test hard/soft-ware |  | mic defect
2019-06-07 | 10:00 | 14:00 | 4:00 | Microphon-Sensor | read data from peak to peak to get decibel (uncalibrated)
2019-06-09 | 10:00 | 16:00 | 6:00 | Design | set up tasks and order them
2019-06-10 | 9:00 | 13:00 | 4:00 | Design | if(treshold reached) send message to server |  | too late to order modules
2019-06-14 | 18:00 | 22:00 | 4:00 | Timestamps | get ntp-timestamp
2019-06-17 | 14:00 | 17:00 | 3:00 | timestamps | get ntp-timestamp |  | ntp-packet sent - no receive
2019-06-20 | 19:00 | 23:00 | 4:00 | Debuggen
2019-06-23 | 10:00 | 15:00 | 5:00 | Server | if(all tivas are connected) {send message to start timer}
2019-06-28 | 16:00 | 22:00 | 6:00 | Clients and Server | timer
2019-06-29 | 12:00 | 20:00 | 8:00 | finalize Client/Server
2019-06-30 | 10:00 | 22:00 | 12:00 | finalize Client/server

## Protokoll_Albrecht
Date | from | to | Difference | To Do | Steps | Infos | Troubles | Fixes
2019-03-04 | 17:50 | 21:00 | 3:10 | Brainstormin, Gitlab Setup | * define project setup & timepath
* Setup gitlab folder structure
* Push SRS Template
2019-03-09 | 11:30 | 14:00 | 2:30 | Code Composer Setup | * Verify installation, test old projects
* Code Composer Studio
* TI-RTOS
2019-03-16 | 11:00 | 15:00 | 4:00 | Research | * research software testing
2019-03-18 | 17:50 | 21:00 | 3:10 | Research Tivas Network capabilities | * Online Research
2019-04-06 | 10:00 | 11:45 | 1:45 | Reinstall Code Composer Studio and TI RTOS | * Unistall old CCS and TIRTOS | Different drivers were making problems on the system |  | Reinstall faster than troubleshooting
* Install CSS and TIRTOS
2019-04-13 | 13:00 | 17:00 | 4:00 | Meeting with Milli | * Discussing used technology
|  |  |  | setup adc | * ADC and Microphone basics
* fist adc steps
2019-04-27 | 13:00 | 16:00 | 3:00 | Doxygen - First Steps | * Download doxygen
* read documentation
* create config
2019-04-29 | 17:50 | 21:00 | 3:10 | Research | * research sound sampling
2019-05-11 | 12:30 | 15:00 | 2:30 | Testing | * basic tests microphone
2019-05-23 | 18:00 | 20:30 | 2:30 | Teammeeting | * current status
* next steps
2018-06-03 | 17:00 | 19:00 | 2:00 | ADC impl | * test new adc impl
2019-06-25 | 8:30 | 10:00 | 1:30 | Soldering new Microphones | * solder both new microphones
| 19:00 | 23:30 | 4:30 | Doxygen | * generate first html files
2019-06-26 | 21:00 | 22:30 | 1:30 | Updating projektverfolgung
| 22:30 | 24:00 | 1:30 | Code Comments | Update Code Documentation for doxygen
2019-06-27 | 18:00 | 23:30 | 5:30 | Testcases | * Create Testcases |  | automatic unit testing
* Prepare Testprotocol
2019-06-28 | 9:00 | 10:00 | 1:00 | Updating projektverfolgung
| 15:00 | 18:00 | 3:00 | Doxygen | * Generate Documentation
| 18:00 | 22:00 | 4:00 | Testcases | * Run Testcaes
* Write Protocol

## Setup
Setup
Kategoriename | Mitarbeitername
Dokumentation | Andreas Mikula
TIVA | Daniel Schinewitz
RASPI | Philip Albrecht
Testcases | Ibrahim Milli
PROJEKTE